## Rakesh OS tasks
S.No. | servers IP | 10.189.251.209 | 10.191.218.102 | 10.191.151.95 | 10.191.151.101 | 10.191.151.98 | 10.191.151.96 | 10.191.151.99 | 10.191.151.102 | 10.191.151.100 | 10.191.151.94 | 10.191.151.97 | 10.191.151.103 | 10.191.151.104 | 10.191.213.55 | 10.191.213.54 | 10.191.213.53 | 10.191.151.115 | 10.191.151.120 | 10.191.151.122 | 10.191.151.121 | 10.191.151.124 | 10.191.151.117 | 10.191.151.118 | 10.191.151.116 | 10.191.151.123 | 10.191.151.119
1 | Application Name | DevSecOps platform / ADOPT UI | DevSecOps platform / ADOPT UI | JIRA | JIRA | Gitlab Community Edition | Nexus OSS Edition | Nexus OSS Edition | SonarQube Community Edition | SonarQube Community Edition | Ansible | Ansible | Jenkins- Slave (Windows) with MSBuild & Selemium | Jenkins- Slave (Linux) + Maven | DB -postgres | DB -postgres | oracle 12c | Jenkins | Jenkins | Jmeter, TestLink | ADOPT services | ADOPT services | Nagios | Nagios | ELK APM | ELK Cluster | Kibana
| rhel OS | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9 | RHEL 7.9
| CPU , | 16 | 16 | 16 CPU , | 16 CPU , | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
| RAM | 16 | 16 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
| HDD | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
| mount point partition creation as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard | available as per standard
3 | user creation as per req of app
4 | NTP configuration
5 | rsyslog configuration
6 | set a root password on all user | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already | default set already
7 | rscd agent installation and configuration
8 | Desktop FAR | done | done | done | done | done | done | done | done | done | done | done | done | done | done |  | done | done | done | done | done | done | done | done | done | done | done
9 | adding packages and yum configuration | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done
10 | set hostname | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done | done
11 | flushed Iptables | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done
12 | set time and hwclock
13 | addmitam user with visudo access
14 | Add detail in BMC portal
15 | CPU ,Memory , disk requiremt | Complete | Complete | Complete | Complete | Complete
16 | /boot must me 1GB | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available | 500 MB available
17 | Public Ip configuration | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done
18 | defaukt gateway ping status | [10 empty] | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done
19 | LVM mount point for database partition | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | ##### | #####
20 | check SCD point
21 | proxy set on all servers | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | done | done | done
22 | OS upgrade to RHEL 7.9 version in all servers | Done | Done | Done | done | done | done | done | done | done | done | done |  | done | done | Done | Done | Done | Done | Done | Done | Done | Done | Done | done | done | done
23 | Selinux policy change to Permissive mode
24 | /etc/host configuration for pre-prod domain names/IP mapping
25 | Environment variable configuration for no_proxy(proxy already in list)
26 | SBI CA certificate import in Linux OS trust store
SBI CA certificate import to all other java trust store including applications

## Installation & Config tracker
S.No | Type | Meghdoot name convention | servers IP | Application Name | Version | Download Software | Installation Status | Java Configure | DB Configure | Port Configuration Status | Nagios agent config | Http Configuration url | Https Configuration Status | Https Configuration url | Port Used | Email Configuration Status | Jenkins & Others Configuration Status | app service start user | Admin User ID | Admin Password | other users | other users pwd | Document Preparation | Remarks
1 | WEB | R0ETADVOPSWP001 | 10.189.251.209 | DevSecOps platform / ADOPT UI | 3.0.0 | Done | Done | Done | NA | Done | Done | Done | Done | https://devopspreprod.statebanktimes.in/ https://devopsdev.statebanktimes.in:9090/demo | 9090
2 | WEB | R0ETADVOPSWP002 | 10.191.218.102 | DevSecOps platform / ADOPT UI | 3.0.0 | Done | Done | Done | S | Done | Done | Done | Done | https://devopspreprod.statebanktimes.in/ https://devopsdev.statebanktimes.in:9090/demo | 9090
3 | APP | R0ETADVOPSAP001 | 10.191.151.95 | JIRA | 8.5.9 | Done | Done | Done | postgres | Done | Done | Done | Done | https://jirapreprod.statebanktimes.in/ | 8085 | [7 empty] | Install - Done, Config- pending
4 | APP | R0ETADVOPSAP002 | 10.191.151.101 | JIRA | 8.5.9 | Done | Done | Done | postgres | Done | Done |  |  |  | 8085
5 | APP | R0ETADVOPSAP003 | 10.191.151.98 | Gitlab Community Edition | 11.6.0 | Done | Done | Done | Done | Done | Done | Done | Done | https://gitlabpreprod.statebanktimes.in/ | 8083 |  |  |  | root | gitlab12345 |  |  | Install - Done, Config- pending
6 | APP | R0ETADVOPSAP004 | 10.191.151.96 | Nexus OSS Edition | 3.28.1-01 | Done | Done | Done | NA | Done | Done | Done | Done | https://nexuspreprod.statebanktimes.in/ | 8082 | [7 empty] | Install - Done, Config- pending
7 | APP | R0ETADVOPSAP005 | 10.191.151.99 | Nexus OSS Edition | 3.28.1-01 | Done | Done | Done | NA | Done | Done | Done | Done | https://nexuspreprod.statebanktimes.in/ | 8082 | [7 empty] | Install - Done, Config- pending
8 | APP | R0ETADVOPSAP006 | 10.191.151.102 | SonarQube Community Edition | 7.9.1 | Done | Done | Done | postgres | Done | Done | Done | Done | https://sonarqubepreprod.statebanktimes.in/ | 9100 |  |  | sonarqube/sonarqube
9 | APP | R0ETADVOPSAP007 | 10.191.151.100 | SonarQube Community Edition | 7.9.1 | Done | Done | Done | postgres | Done | Done | Done | Done | https://sonarqubepreprod.statebanktimes.in/ | 9100 |  |  | sonarqube/sonarqube
10 | APP | R0ETADVOPSAP008 | 10.191.151.94 | Ansible |  | Done | Done |  | NA | Done | Done | NA | NA | NA | 22
11 | APP | R0ETADVOPSAP009 | 10.191.151.97 | Ansible | 12.0.1 | Done | Done | Done | NA | Done | Done | NA | NA | NA | 22
12 | APP | R0ETADVOPSAP010 | 10.191.151.103 | Jenkins- Slave (Windows) with MSBuild & Selemium |  | Done | Done | Done | NA | Done | Done | NA | NA | NA | 4444
|  | R0ETADVOPSAP010 | 10.191.151.103 | MSBuild
|  | R0ETADVOPSAP010 | 10.191.151.103 | Selemium
13 | APP | R0ETADVOPSAP011 | 10.191.151.104 | Jenkins- Slave (Linux) + Maven |  | Done | Done | Done | NA | Done | Done | NA | NA | NA | 5555
|  | R0ETADVOPSAP011 | 10.191.151.104 | Maven |  | Done | Done | Done | NA | Done | Done | NA | NA | NA | NA
14 | DB | R0ETADVOPSDP001 | 10.191.213.55 | DB -postgres -git | 9.6.19 | Done | Done | Done | NA | Done | Done | NA | NA | NA | 5454 |  |  |  | postgres | - |  |  | Install- Done, Config- Done
15 | DB | R0ETADVOPSDP002 | 10.191.213.54 | DB -postgres - other tools | 9.6.19 | Done | Done | Done | NA | Done | Done | NA | NA | NA | 5454 |  |  |  | postgres | - |  |  | Install- Done, Config- Done
16 | DB | R0ETADVOPSDP003 | 10.191.213.53 | oracle 12c |  | Done | Done | Done | NA | Done | Done | NA | NA | NA | 1545
17 | APP | R0ETADVOPSAP022 | 10.191.151.115 | Jenkins | 2.249 | Done | Done | Done | NA | Done | Done | Done | Done | https://jenkinspreprod.statebanktimes.in/ | 8081 |  |  |  | admin | admin |  |  | Install- Done, Config- in progress | Plugins Install- Done, Plugins config- inprogress
18 | APP | R0ETADVOPSAP023 | 10.191.151.120 | Jenkins | 2.249 | Done | Done | Done | NA | Done | Done | Done | Done | https://jenkinspreprod.statebanktimes.in/ | 8081 |  |  |  | admin | admin |  |  | Install- Done, Config- in progress | Plugins Install- Done, Plugins config- inprogress
19 | APP | R0ETADVOPSAP024 | 10.191.151.122 | Jmeter, TestLink | Jmeter- 5.4, Testlink - 1.9.20-9 | Done | Done | Done | NA | Done | Done | Done | Partial Done(configure but need to verify once dns configured by sbi) | https://testlinkpreprod.statebanktimes.in/ | 1090 & 3333 |  |  |  | testuser | test123
20 | APP | R0ETADVOPSAP025 | 10.191.151.121 | ADOPT services & keycloak | 3.0.0/9.0.39 | Done | Done | Done | oracle & postgres | Done | Done | Done, Done | Partial Done(configure but need to verify once dns configured by sbi) | https://devopsservicespreprod.statebanktimes.in/ https://keycloakpreprod.statebanktimes.in/ | 9090 & 6565
21 | APP | R0ETADVOPSAP026 | 10.191.151.124 | ADOPT services & keycloak | 3.0.0/9.0.39 | Done | Done | Done | oracle & postgres | Done | Done | Done, Done | Partial Done(configure but need to verify once dns configured by sbi) | https://devopsservicespreprod.statebanktimes.in/ https://keycloakpreprod.statebanktimes.in/ | 9090 & 6565
22 | APP2 | R0ETADVOPSAP027 | 10.191.151.117 | Nagios | 4.3.2 | Done | Done | Done | NA | Done | Done | Done | Partial Done(configure but need to verify once dns configured by sbi) | https://nagiospreprod.statebanktimes.in/ | 443 |  |  |  | nagios | nagios123 |  |  | Install - Done, Config- pending
23 | APP2 | R0ETADVOPSAP028 | 10.191.151.118 | Nagios | 4.3.2 | Done | Done | Done | NA | Done | Done | Done | Partial Done(configure but need to verify once dns configured by sbi) | https://nagiospreprod.statebanktimes.in/ | 443 |  |  |  | nagios | nagios124 |  |  | Install - Done, Config- pending
24 | APP2 | R0ETADVOPSAP029 | 10.191.151.116 | ELK APM |  | Done | Done | Done | NA | Done | Done | Done |  |  | 443
25 | APP2 | R0ETADVOPSAP030 | 10.191.151.123 | ELK Cluster |  | Done | Done | Done | NA | Done | Done | Done |  |  | 443
26 | APP2 | R0ETADVOPSAP031 | 10.191.151.119 | Kibana |  | Done | Done | Done | NA | Done | Done | Done |  |  | 443
27 | NA | DMZ/UAT | 10.191.206.179:3128 | Repo server | [6 empty] | Done
28 | NA | Proxy ip | 10.191.191.39:3128 | Proxy details
| Server login details | user id - root / root123
non root user - appadmin / appadmin
IMP Points to take care during nstallation and configurartion 1. Application installation port should be opened by FAR Approvals 2. Given Urls should be whitelist in server and desktop 3. Installation and config should be Done using non-root user 4.

## Fortify
10.189.42.240, 10.189.42.241, 10.189.42.242, 10.189.42.243 | 10.191.159.50, 10.191.159.53, 10.191.159.49, 10.191.159.52 | NSPM | tcp/443
10.191.159.49, 10.191.159.52 | 10.189.42.240, 10.189.42.241 | NSPM | tcp/22
10.189.42.242, 10.189.42.243 | 10.191.159.115, 10.191.159.116 | NSPM | tcp/443, tcp/50000
10.191.159.49, 10.191.159.52 | 10.189.42.245 | NSPM | tcp/8443
10.189.42.245 | 10.191.159.49, 10.191.159.52 | NSPM | tcp/443
10.30.36.121, 10.30.36.122, 10.30.36.123, 10.30.36.124, 10.30.36.125, 10.30.36.81, 10.30.36.83, 10.30.36.74 | 10.189.42.245 | NSPM | tcp/8443
jenkins workspace location on slave- /opt/jenkins/workspace
Fortify Home on slave- /opt/Fortify/Fortify_SCA_and_Apps_19.1.0/bin
Linux Slave : 10.189.42.241
exe path : /opt/Fortify/Fortify_SCA_and_Apps_19.1.0/bin
java -jar slave.jar -jnlpUrl https://scanmgmtsrv.scrs.sbi.co.in:8443/jenkins/computer/scanclstnode4.scrs.sbi.co.in/slave-agent.jnlp -secret 34b837d22576435d68459e520275afb469c40b2d10fe9fd34e4919e05a820986 -workDir "C:\Jenkins"

## EPM & Fortify FAR
DEV & UAT
Fortify
Source | Destination | Port | NSPM Comments
10.189.42.240, 10.189.42.241, 10.189.42.242, 10.189.42.243 | 10.191.159.50, 10.191.159.53, 10.191.159.49, 10.191.159.52 | tcp/443 | FAR to access code repository and other build tools (nexus etc.) if required during code build process
10.191.159.49, 10.191.159.52 | 10.189.42.240, 10.189.42.241 | tcp/22 | FAR for configuring LINUX scanner servers with DevOps Jenkins
10.189.42.242, 10.189.42.243 | 10.191.159.115, 10.191.159.116 | tcp/443, tcp/50000 | FAR for configuring Windows scanner servers with Devops Jenkins
10.191.159.49, 10.191.159.52 | 10.189.42.245 | tcp/8443 | For SSC API communication
10.189.42.245 | 10.191.159.49, 10.191.159.52 | tcp/443 | Communication from linux scanner and SSC to ETA Jenkins
10.30.36.121, 10.30.36.122, 10.30.36.123, 10.30.36.124, 10.30.36.125, 10.30.36.81, 10.30.36.83, 10.30.36.74 | 10.189.42.245 | tcp/8443 | For accessing SSC portal on department desktops for viewing and auditing scan reports.
EPM
10.191.159.48,10.191.159.51,10.30.36.125,10.30.36.121 | 10.191.154.29 | tcp/8443
Pre-Prod
Fortify
Source | Destination | Port | NSPM Comments
10.189.42.240, 10.189.42.241, 10.189.42.242, 10.189.42.243 | Gitlab - 10.191.151.98, Nexus - 10.191.151.96, 10.191.151.99 | tcp/443 | FAR to access code repository and other build tools (nexus etc.) if required during code build process
Master - 10.191.151.115, 10.191.151.120 Slave - 10.191.151.104 | 10.189.42.240, 10.189.42.241 | tcp/22 | FAR for configuring LINUX scanner servers with DevOps Jenkins
10.189.42.242, 10.189.42.243 | 10.191.151.103 | tcp/443, tcp/50000 | FAR for configuring Windows scanner servers with Devops Jenkins
Master - 10.191.151.115, 10.191.151.120 Slave - 10.191.151.104 | 10.189.42.245 | tcp/8443 | For SSC API communication
10.189.42.245 | Master - 10.191.151.115, 10.191.151.120 Slave - 10.191.151.104 | tcp/443 | Communication from linux scanner and SSC to ETA Jenkins
10.30.36.121, 10.30.36.122, 10.30.36.123, 10.30.36.124, 10.30.36.125, 10.30.36.81, 10.30.36.83, 10.30.36.74 | 10.189.42.245 | tcp/8443 | For accessing SSC portal on department desktops for viewing and auditing scan reports.
EPM
Desktop - 10.30.36.121, 10.30.36.122, 10.30.36.123, 10.30.36.124, 10.30.36.125, 10.30.36.81, 10.30.36.83, 10.30.36.74 ADOPT Services server - 10.191.151.121, 10.191.151.124 | 10.191.154.29 | tcp/8443 | EPM connection with dekstop and Adopt Servers

## Preprd SSL
S. No | Name of tool | IP address of the server tool is installed(DEV) | IP address of the server tool is installed(UAT) | S.No | Application Name | servers IP | URLS
1 | Jira | 10.191.159.48 | 10.191.159.51 | 1 | DevSecOps platform / ADOPT UI | 10.189.251.209 | https://devopspreprod.statebanktimes.in/
2 | ADOPT Portal - tomcat | 10.191.159.48 | 10.191.159.51 | 2 | DevSecOps platform / ADOPT UI | 10.191.218.102
3 | SonarQube | 10.191.159.48 | 10.191.159.51 | 3 | JIRA | 10.191.151.95 | https://jirapreprod.statebanktimes.in/
4 | Jenkins | 10.191.159.49 | 10.191.159.52 | 4 | JIRA | 10.191.151.101
5 | Jmeter | 10.191.159.49 | 10.191.159.52 | 5 | Gitlab Community Edition | 10.191.151.98 | https://gitlabpreprod.statebanktimes.in/
6 | nexus | 10.191.159.49 | 10.191.159.52 | 6 | Nexus OSS Edition | 10.191.151.96 | https://nexuspreprod.statebanktimes.in/
7 | Gitlab | 10.191.159.50 | 10.191.159.53 | 7 | Nexus OSS Edition | 10.191.151.99
8 | ELK APM | 10.191.159.50 | 10.191.159.53 | 8 | SonarQube Community Edition | 10.191.151.102 | https://sonarqubepreprod.statebanktimes.in/
9 | Kibana | 10.191.159.50 | 10.191.159.53 | 9 | SonarQube Community Edition | 10.191.151.100
10 | Nagios | 10.191.159.50 | 10.191.159.53 | 10 | KeyCloak | 10.191.151.97 | https://keycloakpreprod.statebanktimes.in/
11 | testlink | 10.191.154.217 | 10.191.154.218 | 11 | Jenkins | 10.191.151.115 | https://jenkinspreprod.statebanktimes.in/
|  |  |  | 12 | Jenkins | 10.191.151.120
|  |  |  | 13 | TestLink | 10.191.151.122 | https://testlinkpreprod.statebanktimes.in/
|  |  |  | 14 | ADOPT services | 10.191.151.121 | https://devopsservicespreprod.statebanktimes.in/
|  |  |  | 15 | ADOPT services | 10.191.151.124
|  |  |  | 16 | Nagios | 10.191.151.117 | https://nagiospreprod.statebanktimes.in/
|  |  |  | 17 | Nagios | 10.191.151.118
|  |  |  | 18 | ELK APM | 10.191.151.116 | https://elkapmpreprod.statebanktimes.in/
|  |  |  | 19 | ELK Cluster | 10.191.151.123 | https://elkclusterpreprod.statebanktimes.in/
|  |  |  | 20 | Kibana | 10.191.151.119 | https://kibanapreprod.statebanktimes.in/

## Update SBI Load balancer & Ip's
Sl.No | Type | Meghdoot name convention | IP Address | Tools | OS
1 | WEB | R0ETADVOPSWP001 | 10.189.251.209 | DevSecOps platform / ADOPT UI / Keycloak | RHEL 7.9
2 | WEB | R0ETADVOPSWP002 | 10.191.218.102 | DevSecOps platform / ADOPT UI / Keycloak | RHEL 7.9
3 | APP | R0ETADVOPSAP001 | 10.191.151.95 | JIRA | RHEL 7.9
4 | APP | R0ETADVOPSAP002 | 10.191.151.101 | JIRA | RHEL 7.9
5 | APP | R0ETADVOPSAP003 | 10.191.151.98 | Gitlab Community Edition | RHEL 7.9
6 | APP | R0ETADVOPSAP004 | 10.191.151.96 | Nexus OSS Edition | RHEL 7.9
7 | APP | R0ETADVOPSAP005 | 10.191.151.99 | Nexus OSS Edition | RHEL 7.9
8 | APP | R0ETADVOPSAP006 | 10.191.151.102 | SonarQube Community Edition | RHEL 7.9
9 | APP | R0ETADVOPSAP007 | 10.191.151.100 | SonarQube Community Edition | RHEL 7.9
10 | APP | R0ETADVOPSAP008 | 10.191.151.94 | Ansible | RHEL 7.9
11 | APP | R0ETADVOPSAP009 | 10.191.151.97 | Ansible | RHEL 7.9
12 | APP | R0ETADVOPSAP010 | 10.191.151.103 | Jenkins- Slave (Windows) with MSBuild & Selemium | Microsoft Windows Server 2016
13 | APP | R0ETADVOPSAP011 | 10.191.151.104 | Jenkins- Slave (Linux) + Maven | RHEL 7.9
14 | DB | R0ETADVOPSDP001 | 10.191.213.55 | DB -postgres | RHEL 7.9
15 | DB | R0ETADVOPSDP002 | 10.191.213.54 | DB -postgres | RHEL 7.9
16 | DB | R0ETADVOPSDP003 | 10.191.213.53 | oracle 12c | RHEL 7.9
17 | APP | R0ETADVOPSAP022 | 10.191.151.115 | Jenkins | RHEL 7.9
18 | APP | R0ETADVOPSAP023 | 10.191.151.120 | Jenkins | RHEL 7.9
19 | APP | R0ETADVOPSAP024 | 10.191.151.122 | Jmeter, TestLink | RHEL 7.9
20 | APP | R0ETADVOPSAP025 | 10.191.151.121 | ADOPT Services | RHEL 7.9
21 | APP | R0ETADVOPSAP026 | 10.191.151.124 | ADOPT Services | RHEL 7.9
22 | APP2 | R0ETADVOPSAP027 | 10.191.151.117 | Nagios | RHEL 7.9
23 | APP2 | R0ETADVOPSAP028 | 10.191.151.118 | Nagios | RHEL 7.9
24 | APP2 | R0ETADVOPSAP029 | 10.191.151.116 | ELK APM | RHEL 7.9
25 | APP2 | R0ETADVOPSAP030 | 10.191.151.123 | ELK Cluster | RHEL 7.9
26 | APP2 | R0ETADVOPSAP031 | 10.191.151.119 | Kibana | RHEL 7.9
LoadBalancer Details :
LoadBalancer | IP | Loadbalancer's Tools
LB01 | 10.191.146.35 | DevSecOps platform / ADOPT UI / KeyCloak
LB02 | 10.191.146.36 | JIRA
LB03 | 10.191.146.37 | Nexus OSS Edition
LB04 | 10.191.146.38 | SonarQube Community Edition
LB05 | 10.191.146.39 | Jenkins
LB06 | 10.191.146.40 | ADOPT Services
LB07 | 10.191.146.41 | Nagios
LB08 | 10.191.148.221 | Ansible

## Preprod-FAR-review_v06
Sr no | Meghdoot name convention | Destination | Applications | Destination Ports | HTTPS port | Application Source connected | Source | Source port | Remarks
| R0ETADVOPSWP001 | 10.189.251.209 | DevSecOps platform / ADOPT UI + Tomcat(9090) / Keycloak(6565) | 9090, 6565, 22, 8087 | 443 | Desktop, Nagios | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP001 | 10.191.218.102 | DevSecOps platform / ADOPT UI + Tomcat(9090) / Keycloak(6565) | 9090, 6565, 22, 8087 | 443 | Desktop, Nagios | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP001 | 10.191.151.95 | JIRA | 8085, 22, 8087 | 443 | Desktop, ADOPT UI, ADOPT services, Nagios | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.189.251.209, 10.191.218.102, 10.191.151.121, 10.191.151.124, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP002 | 10.191.151.101 | JIRA | 8085, 22, 8087 | 443 | Desktop, ADOPT UI, ADOPT services, Nagios | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.189.251.209, 10.191.218.102, 10.191.151.121, 10.191.151.124, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP002 | 10.191.151.98 | Gitlab Community Edition | 8083, 22, 8087 | 443 | Desktop, Jenkins, ADOPT UI, ADOPT services, Nagios, Jenkins Slave(103, 104) | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.189.251.209, 10.191.218.102, 10.191.151.115, 10.191.151.120 , 10.191.151.121, 10.191.151.124, 10.191.151.117, 10.191.151.118, 10.191.151.103, 10.191.151.104 | Any
| R0ETADVOPSAP003 | 10.191.151.96 | Nexus OSS Edition | 8082, 22, 8087 | 443 | Desktop, Jenkins, Ansible, Nagios, | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.115, 10.191.151.120 , 10.191.151.94, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP004 | 10.191.151.99 | Nexus OSS Edition | 8082, 22, 8087 | 443 | Desktop, Jenkins, Ansible, Nagios | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.115, 10.191.151.120 , 10.191.151.94, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP005 | 10.191.151.102 | SonarQube Community Edition | 9100, 22, 8087 | 443 | Desktop, ADOPT UI, Jenkins, Jenkins Slave(103, 104), ADOPT services, Nagios | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.189.251.209, 10.191.218.102, 10.191.151.115, 10.191.151.120, 10.191.151.121, 10.191.151.124, 10.191.151.117, 10.191.151.118, 10.191.151.103, 10.191.151.104 | Any
| R0ETADVOPSAP006 | 10.191.151.100 | SonarQube Community Edition | 9100, 22, 8087 | 443 | Desktop, ADOPT UI, Jenkins, Jenkins Slave(103, 104), ADOPT services, Nagios | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.189.251.209, 10.191.218.102, 10.191.151.115, 10.191.151.120, 10.191.151.121, 10.191.151.124, 10.191.151.117, 10.191.151.118, 10.191.151.103, 10.191.151.104 | Any
| R0ETADVOPSAP008 | 10.191.151.94 | Ansible | 22, 8087, 13070 | NA | Desktop only (22), Nagios (8087), Jenkins, Jenkins Slave(103, 104) -13070 | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.115, 10.191.151.120, 10.191.151.96, 10.191.151.99, 10.191.151.117, 10.191.151.118, 10.191.151.103, 10.191.151.104 | Any
| R0ETADVOPSAP009 | 10.191.151.97 | Ansible | 8089, 22, 8087 | 443 | Desktop, Jenkins, Tomcat(ADOPT UI), ADOPT services, GitLab, JIRA, SonarQube, TestLink, Nagios | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.115, 10.191.151.120, 10.189.251.209, 10.191.218.102, 10.191.151.121, 10.191.151.124, 10.191.151.98, 10.191.151.95,10.191.151.101, 10.191.151.102, 10.191.151.100, 10.191.151.122, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP010 | 10.191.151.103 | Jenkins- Slave (Windows) with MSBuild & Selemium | 4444, 22, 8087 | NA | Desktop, jenkins, Nagios, Nexus, SonarQube | desktop (10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125) server - 10.191.151.115, 10.191.151.120, 10.191.151.117, 10.191.151.118 10.191.151.96, 10.191.151.99, 10.191.151.102, 10.191.151.100 | Any
| R0ETADVOPSAP011 | 10.191.151.104 | Jenkins- Slave (Linux) + Maven +UI | 5555, 22, 8087 | NA | Desktop, jenkins, Nagios, Nexus, SonarQube | desktop (10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125) server - 10.191.151.115, 10.191.151.120, 10.191.151.117, 10.191.151.118 10.191.151.96, 10.191.151.99, 10.191.151.102, 10.191.151.100 | Any
| R0ETADVOPSDP001 | 10.191.213.55 | DB -postgres - Git | 5454, 22, 8087 | NA | Desktop, Gitlab, Nagios | desktop (10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125) Server - 10.191.151.98, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSDP002 | 10.191.213.54 | DB -postgres - other tools | 5454, 22, 8087 | NA | Desktop, Jira, keycloak, sonarqube, Nagios | desktop (10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125) Server - 10.191.151.95, 10.191.151.101, 10.191.151.97, 10.191.151.102, 10.191.151.100, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSDP003 | 10.191.213.53 | oracle 12c | 1545, 22, 8087 | NA | Desktop, ADOPT UI, ADOPT Services, Nagios | desktop (10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125) server - 10.189.251.209, 10.191.218.102, 10.191.151.121, 10.191.151.124, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP022 | 10.191.151.115 | Jenkins | 8081, 22, 8087, 50000 | 443 | Desktop, Tomcat(ADOPT UI), ADOPT Services, Nagios, Gitlab, Keycloak Jenkins agent port (50000) | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.189.251.209, 10.191.218.102, 10.191.151.121, 10.191.151.124, ,10.191.151.117, 10.191.151.118, 10.191.151.98, 10.191.151.97 | Any
| R0ETADVOPSAP023 | 10.191.151.120 | Jenkins | 8081, 22, 8087, 50000 | 443 | Desktop, Tomcat(ADOPT UI), ADOPT Services, Nagios, Gitlab, Keycloak Jenkins agent port (50000) | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.120, 10.191.151.96, 10.191.151.99, 10.189.251.209, 10.191.218.102, 10.191.151.94, 10.191.151.97, 10.191.151.98, 10.191.151.95, 10.191.151.101, 10.191.151.122 ,10.191.151.117 | Any
| R0ETADVOPSAP024 | 10.191.151.122 | Jmeter, TestLink | 1090, 3333, 22, 8087 | 443(Testlink) | Jmeter - Desktop, Jenkins, Nagios Testlink - Desktop, Tomcat(ADOPT UI), ADOPT services, Keycloak, Nagios | desktop (10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125)10.189.251.209 server - 10.191.151.115, 10.191.151.120, 10.189.251.209, 10.191.218.102, 10.191.151.121, 10.191.151.124, 10.191.151.97, 10.191.151.117, 10.191.151.118 | Any
| R0ETADVOPSAP025 | 10.191.151.121 | ADOPT services + Tomcat | 9090, 22, 8087, 1307 | 443 | Desktop, Jenkins, Tomcat(ADOPT UI), Nagios, Ansible(1307) | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.115,10.191.151.120, 10.189.251.209, 10.191.218.102, ,10.191.151.117, 10.191.151.118, 10.191.151.94 | Any
| R0ETADVOPSAP026 | 10.191.151.124 | ADOPT services + Tomcat | 9090, 22, 8087, 1307 | 443 | Jenkins, Tomcat(ADOPT UI), ADOPT services, Ansible(1307) | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 server - 10.191.151.115,10.191.151.120, 10.189.251.209, 10.191.218.102, ,10.191.151.117, 10.191.151.118, 10.191.151.94 | Any
| R0ETADVOPSAP027 | 10.191.151.117 | Nagios | 8086,8087,161,162, 22 | 443 | Desktop | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 Server - 10.189.251.209, 10.191.218.102, 10.191.151.121, 10.191.151.124, 10.191.151.98, 10.191.151.95, 10.191.151.101, 10.191.151.115,10.191.151.120, 10.191.151.94, 10.191.151.122, 10.191.151.96, 10.191.151.99, 10.191.213.53, 10.191.213.54, 10.191.213.55, 10.191.151.102 ,10.191.151.100, 10.191.151.103, 10.191.151.104, 10.191.151.97, 10.191.151.102, 10.191.151.100, 10.191.151.117, 10.191.151.118 | Any | 8086 for Nagios, 8087 NRPE to connect client, 161 & 162 for SNMP
| R0ETADVOPSAP028 | 10.191.151.118 | Nagios | 8086,8087,161,162, 22 | 443 | Desktop | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 Server - 10.189.251.209, 10.191.218.102, 10.191.151.121, 10.191.151.124, 10.191.151.98, 10.191.151.95, 10.191.151.101, 10.191.151.115,10.191.151.120, 10.191.151.94, 10.191.151.122, 10.191.151.96, 10.191.151.99, 10.191.213.53, 10.191.213.54, 10.191.213.55, 10.191.151.102 ,10.191.151.100, 10.191.151.103, 10.191.151.104, 10.191.151.97, 10.191.151.102, 10.191.151.100, 10.191.151.117, 10.191.151.118 | Any | 8086 for Nagios, 8087 NRPE to connect client, 161 & 162 for SNMP
| R0ETADVOPSAP029 | 10.191.151.116 | ELK APM | 8201, 22 | 443 | Desktop | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 Server -NA | Any
| R0ETADVOPSAP030 | 10.191.151.123 | ELK Cluster | 9200, 5044, 5062, 22 | 443 | ELK APM | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 Server -10.191.151.116 | Any
| R0ETADVOPSAP031 | 10.191.151.119 | Kibana(5602 in dev and UAT) | 5062, 22 | 443 | ELK APM | desktop -10.30.36.121, 10.30.36.122,10.30.36.123,10.30.36.124, 10.30.36.125 Server - 10.191.151.116 | Any
Note on G2: Bhaskar R Reddy: Nagios NRPE port is missing for all FARs. ---Done (tarun)
Note on G11: Bhaskar R Reddy: Wrong Port (22) for Jenkins, Nagios, Jenkins slave. ---Done (tarun)
Note on G13: Bhaskar R Reddy: Desktop port number missing/wrong ? --- Done (tarun)
Note on G14: Bhaskar R Reddy: Desktop port number missing/wrong ? --- Done (tarun)
Note on G21: Bhaskar R Reddy: Ansible port missing. ---Done (Tarun)
Note on G22: Bhaskar R Reddy: Ansible port missing. ---Done (Tarun)
Note on G23: Bhaskar R Reddy: why these tools need to connect Nagios? ---Done (Tarun)
Note on G24: Bhaskar R Reddy: why these tools need to connect Nagios? ---Done (Tarun)

## Preprod-FAR-review_v07
Sr no | Meghdoot name convention | Destination | Applications | Destination Ports | Application Source connected | Source | Source port | Remarks
1 | R0ETADVOPSWP001 | 10.189.251.209 | DevSecOps platform / ADOPT UI + Tomcat(9090) / Keycloak(6565) | 9090, 6565 |  |  | Any
2 | R0ETADVOPSAP001 | 10.191.218.102 | DevSecOps platform / ADOPT UI + Tomcat(9090) / Keycloak(6565) | 9090, 6565 |  |  | Any
3 | R0ETADVOPSAP001 | 10.191.151.95 | JIRA | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
4 | R0ETADVOPSAP002 | 10.191.151.101 | JIRA | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
5 | R0ETADVOPSAP002 | 10.191.151.98 | Gitlab Community Edition | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
6 | R0ETADVOPSAP003 | 10.191.151.96 | Nexus OSS Edition | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
7 | R0ETADVOPSAP004 | 10.191.151.99 | Nexus OSS Edition | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
8 | R0ETADVOPSAP005 | 10.191.151.102 | SonarQube Community Edition | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
9 | R0ETADVOPSAP006 | 10.191.151.100 | SonarQube Community Edition | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
10 | R0ETADVOPSAP010 | 10.191.151.103 | Jenkins- Slave (Windows) with MSBuild & Selemium | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
11 | R0ETADVOPSAP011 | 10.191.151.104 | Jenkins- Slave (Linux) + Maven +UI | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
12 | R0ETADVOPSAP022 | 10.191.151.115 | Jenkins | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
13 | R0ETADVOPSAP023 | 10.191.151.120 | Jenkins | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
14 | R0ETADVOPSAP024 | 10.191.151.122 | Jmeter, TestLink | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
15 | R0ETADVOPSAP025 | 10.191.151.121 | ADOPT services + Tomcat | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any
16 | R0ETADVOPSAP026 | 10.191.151.124 | ADOPT services + Tomcat | 6565 | keycloak | 10.189.251.209, 10.191.218.102 | Any